## Slide 1
Process Inspector
How we built it — the research, the delivery approach, and what we change next
Delivery review · 6 – 27 July 2026 · workflow platform team

## Slide 2
WHAT WE BUILT
One console for every stuck process
– The job it does: an on-call engineer finds, diagnoses and fixes a failed process instance in one place — instead of an SSH session, a database query and a guess.
– Multi-engine by design: all Flowable environments (test, staging, production) in one search, each labeled with its environment colour.
– Safe by construction: read-only by default; every fix is role-gated, requires a stated reason, and is written to an audit trail the incumbent tool does not have.
– Zero footprint on the engines: integrates strictly through the public Flowable REST API — no database access, no plugin, no agent to install.
– Status today: live on the demo host, released as versioned container images, with a nightly full-system test run.
Process Inspector — delivery review
1

## Slide 3
OUTCOME
Three weeks, from empty repository to released product
22
calendar days
6 – 27 July 2026
119
pull requests merged
every one green in CI first
111k
lines of product code
70k backend · 41k frontend
2,100+
automated tests
incl. 49 against real engines
117
tracked requirements
each traced to code and tests
14,700
lines of living specification
kept in step with the code
Delivered by a small team working with AI coding agents under a fixed set of engineering rules.
Process Inspector — delivery review
2

## Slide 4
TIMELINE
How the three weeks were spent
Day 1
Research and specification only
Two market studies, an expert panel and a 14-seat review board — no product code written.
Week 1
Core product (M0 – M4)
Engine registry, cross-engine search, instance detail with diagram, corrective actions, audit trail, roles.
Week 2
v1 close-out and release
Bulk operations, hardening, container release pipeline, live demo environment, parallel CI.
Week 3
Demand-driven v2
Shared team views, deep paging, runtime engine administration, identity and access, incident ledger.
Week 4
Adversarial review and fix
Whole-application review; 17 findings implemented and merged; framework versions brought current.
Process Inspector — delivery review
3

## Slide 5
HOW WE STARTED · RESEARCH
We started with a market study, not a prototype
– Study 1 — the incumbent. A full feature and permission inventory of IBM BAW Process Inspector, together with its documented weaknesses: no saved searches, no search by instance ID or variable, manual-only bulk, and no audit trail of administrator actions.
– Study 2 — the field. Seven comparable tools (Camunda, Temporal, Flowable Control, Conductor, Airflow, AWS Step Functions, Azure Durable Functions) reduced to twelve patterns the whole industry has converged on.
– Study 3 — the platform. What the Flowable REST API can and cannot actually do — established by experiment against a real engine, before anything was promised.
– Output of day one: a specification with a glossary, numbered design principles and an explicit list of things we would not build.
Process Inspector — delivery review
4

## Slide 6
HOW WE STARTED · REVIEW
Then we reviewed the specification like a board
– Round 1 — four expert seats. Workflow-engine specialist, senior support engineer, lead developer and UX expert each reviewed independently, then the findings were reconciled into one specification.
– Round 2 — a fourteen-seat review board. Product owner, business analyst, architect, DevOps, test manager, usability experts and day-shift, L2 and L3 support staff. Roughly 130 findings.
– Reconciliation, not averaging. Where seats disagreed the conflict was recorded and decided in writing — including two features cut from the first release on the product owner’s argument.
– Result: 117 numbered, prioritised requirements and 3 recorded architecture decisions. Every later change refers back to a requirement number.
– Cost: about one day of elapsed time.
Process Inspector — delivery review
5

## Slide 7
HOW WE STARTED · RETURN
What that day of research paid for
– Six correctness traps found before any product code. Most serious: the engine returns failed-job lists ten at a time, so a naive implementation lets a broken process instance appear healthy. Every competitor-grade tool has to solve this; we knew it on day one.
– Four expensive dead ends refused up front. A query language, an undo-able change preview, live streaming search and engine-internals reporting were all specified away — the engine cannot support them, and each would have cost weeks to discover.
– Business blind spots caught early. The first specification had no success measures, no release gate and no rollout plan. The product owner’s seat added them before build, not after pilot.
– “Adjectives where numbers belong.” Every limit, timeout and threshold was rewritten as a testable number — which is why they could later be enforced automatically.
Process Inspector — delivery review
6

## Slide 8
APPROACH · OPERATING MODEL
The specification is the system of record
– Three documents, three questions. What the product does · how and why it is built that way · when each piece lands. Nothing lives in someone’s head.
– The lockstep rule. A change in behaviour updates the matching document section in the same change. A change that does not is not finished.
– Traceability. One matrix links every requirement to the code that implements it and the test that proves it — which is what makes an audit or a compliance question answerable in minutes.
– Why it matters commercially. Any contributor — a new hire or an AI agent — reads the rule instead of guessing, and reviews argue about the decision rather than the diff. This is the single practice that made the pace possible.
Process Inspector — delivery review
7

## Slide 9
WHAT WORKED BEST · 1 OF 3
Small, complete slices — never a big-bang integration
– Every feature was cut into four to six slices, each one independently reviewable, releasable and demonstrable on its own.
– 119 changes in 22 days — the average change stayed small enough to be reviewed properly rather than waved through.
– No long-lived branches. Work merged the day it was written, so two work streams never spent a week diverging.
– Evidence: the five largest second-phase features — shared team views, deep result paging, runtime engine administration, identity and access, and the incident ledger — each went from design lock to complete within one to two days.
– The trade we accepted: more design decisions up front, in exchange for near-zero integration risk at the end.
Process Inspector — delivery review
8

## Slide 10
WHAT WORKED BEST · 2 OF 3
Guardrails are what make speed safe
– A short list of non-negotiable rules covers the ways this product could do real damage: never write to an engine’s database, every corrective action audited and role-gated, database schema only through reviewed migrations.
– The interface between frontend and backend is generated, not hand-written. The two halves are structurally incapable of drifting apart — a whole class of defect simply cannot occur.
– Formatting and code standards are build failures, not review comments. Nobody spends attention on style.
– “Done” means the build is green on the merged commit — a successful upload is not success. This one definition removed most of the “it works on my machine” traffic.
Process Inspector — delivery review
9

## Slide 11
WHAT WORKED BEST · 3 OF 3
Automating the feedback loop, not just the typing
– Build and test time: about 25 minutes → 3 minutes 45. Achieved by running the suite across six parallel build machines. Fast feedback changes behaviour; slow feedback gets skipped.
– A realistic environment on demand. Real Flowable engines start in containers for the tests. Engine behaviour is never faked — which is how the truncation traps stay caught.
– Usability tested before shipping. Scripted incident missions are driven against the real user interface by test agents; a surface ships when the mission success rate clears an agreed bar.
– Independent review on every design and change. Separate AI review models act as a second and third opinion at negligible cost — they caught real defects the author had signed off.
Process Inspector — delivery review
10

## Slide 12
QUALITY
The evidence behind “it works”
1,231
backend tests
49
against real engines
no simulated engine
808
frontend unit tests
64
browser journeys
incl. accessibility
– Nightly full-system run against the complete engine matrix, with a watchdog that raises an alarm if the nightly run itself fails to start.
– Every corrective action is proven against a genuinely failing process, not a stubbed response — the failure modes we advertise are the ones we have actually reproduced.
– Accessibility and visual checks run in the same pipeline as the functional tests, so a regression blocks the merge.
Process Inspector — delivery review
11

## Slide 13
LESSONS
What cost us time — the honest list
– Documentation drift. One sprint shipped seven fixes without updating the plan or closing the ticket. It was found by a human re-reading the document — the process did not catch it.
– A shared working copy. Parallel work streams changed the same checkout underneath each other, producing confusing failures that were not code defects.
– Collisions with unrelated projects on the same host. A network port held by another team’s container looked like an intermittent test failure for a day before it was diagnosed.
– Review substitution under quota limits. When the designated review model was unavailable, one run improvised a different reviewer and effectively graded its own work. No defect resulted, but the control had failed.
– Implied steps get skipped. Automated contributors reliably omitted one formatting check whenever it was not named explicitly in the task.
Process Inspector — delivery review
12

## Slide 14
IMPROVEMENTS
Six changes to the way we work
1
Make the document update a merge check
Drift becomes impossible rather than unlikely; removes the reliance on a reviewer’s memory.
2
One isolated working copy per work stream
Enforced by tooling, not convention — removes a whole class of phantom failure.
3
Reserve a host port range per project
Checked automatically before a build machine starts; ends cross-project interference.
4
Named reviewers only
If the designated reviewer is unavailable the merge waits. No self-grading, ever.
5
Every gate spelled out in the task brief
Assume nothing is implied — the cheapest fix on this list.
6
Track deferred human actions as owned items
Backup activation and production cut-over are named owners with dates, not footnotes in a plan.
Process Inspector — delivery review
13

## Slide 15
NEXT
What we would scale — and what we need from you
– The method transfers to other products. Research and panel review first · numbered requirements · thin slices · hard automated gates. None of it is specific to this product.
– Highest-leverage practices to reuse elsewhere: generated interface contracts, a realistic containerised test environment, and parallel build capacity.
– Decisions we need sponsored: three engines onboarded for the pilot including one production engine and its signed checklist; activation of the audit-store backup and recovery procedure; and the demand evidence that unlocks the remaining automation features.
– The ask: name the pilot owner and the three engines, and give us a date for the production onboarding review.
Questions
Process Inspector — delivery review
14